## Intern Task Plan
Intern No. | Role | Task Title | Description | Start Date | Deadline | Resources
Shivani Vinod Mahalle | Frontend | Design Homepage (UI/UX) | Design a visually attractive homepage with animations and responsive layout. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Krish Gupta | Frontend | Create Login/Signup Page | Implement user login/signup forms with validation and responsiveness. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Nikhil Rokade | Database | Design Database Schema | Create ER diagram for users, bookings, destinations and payments. | 2025-08-05 | 2025-08-08 | https://www.mysqltutorial.org/mysql-basics.aspx/
Vaidehi Bhagane | Database | Setup MySQL/PostgreSQL | Install and configure DB with tables, relationships. | 2025-08-05 | 2025-08-08 | https://www.mysqltutorial.org/mysql-basics.aspx/
Tejshri Ashok Walunj | Frontend | Design Destination Listing Page | Build a dynamic listing of destinations with filters and sorting. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Ashwini Vinod Mahalle | Frontend | Develop Booking Page UI | Interactive booking interface with calendar, pricing and review section. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Pankaj Yogesh Gangurde | Database | Seed Sample Data | Add sample data for testing: destinations, users, etc. | 2025-08-05 | 2025-08-08 | https://www.mysqltutorial.org/mysql-basics.aspx/
Vaishnavi gentyala | Frontend | Create Contact/About Page | Static page with animation effects and contact form. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Onkar Tatyaso Awate | Frontend | Develop User Dashboard UI | Create a dashboard to show bookings, profile and preferences. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Abhijeet Kokare | Database | Create Stored Procedures | Procedures for booking, cancellations, etc. | 2025-08-05 | 2025-08-08 | https://www.mysqltutorial.org/mysql-basics.aspx/
Niranjan Shirish Desai | Database | Database Optimization | Indexing, query optimization for faster access. | 2025-08-05 | 2025-08-08 | https://www.mysqltutorial.org/mysql-basics.aspx/
Akshata Dattatray Lonari | Database | Secure DB Access | Limit access, roles and encryption for sensitive data. | 2025-08-05 | 2025-08-08 | https://www.mysqltutorial.org/mysql-basics.aspx/
Deepesh saini | Backend | Admin Panel APIs | Admin can login, post blogs, and see bookings made by users. | 2025-08-05 | 2025-08-08 | https://www.geeksforgeeks.org/rest-api-using-python-flask-and-mysql/
vijay kumar | Frontend | Integrate Frontend APIs | Fetch destination, booking & login data from backend. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Akash Gawali | Backend | Booking Management APIs | User bookings create/update/delete, validation & response. | 2025-08-05 | 2025-08-08 | https://www.geeksforgeeks.org/rest-api-using-python-flask-and-mysql/
Aishwarya Bargaje | Database | Design Database Schema | Create ER diagram for users, bookings, destinations and payments. | 2025-08-05 | 2025-08-08 | https://www.mysqltutorial.org/mysql-basics.aspx/
Raj Laxman Singh | Frontend | Design Homepage (UI/UX) | Design a visually attractive homepage with animations and responsive layout. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Mohitha.M. | Frontend | Create Login/Signup Page | Implement user login/signup forms with validation and responsiveness. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer
Shivtej Madan Bhandekari | Frontend | Design Destination Listing Page | Build a dynamic listing of destinations with filters and sorting. | 2025-08-05 | 2025-08-08 | https://developer.mozilla.org/en-US/docs/Learn/Front-end_web_developer